Work Breakdown Structure (WBS)

Student Project Portfolio & Showcase App  |  Individual project  |  Effort figures are planning estimates

| WBS ID | Task | Depends on | Effort | Deliverable | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Requirements Engineering |  |  |  |  |
| 1.1 | Understand problem statement #04 and identify actors | Problem statement | 0.5 d | Actor list | Done |
| 1.2 | Draw UML use-case diagram (UC-01 – UC-07) | 1.1 | 0.5 d | UseCase_Diagram.pdf | Done |
| 1.3 | Write use-case flow specification (UC-05) | 1.2 | 0.5 d | UseCase_Flow doc | Done |
| 1.4 | Write FR/NFR requirements table | 1.2 | 1 d | Requirements_Table.docx | Done |
| 1.5 | Build RTM | 1.4 | 0.5 d | RTM_Table.docx | Done |
| 2 | Architecture & Design |  |  |  |  |
| 2.1 | Analyse Layered, Microservices, Client-Server styles | 1.4 | 0.5 d | Style comparison | Done |
| 2.2 | Select architecture and identify components | 2.1 | 0.5 d | Component list | Done |
| 2.3 | Create UML component diagram | 2.2 | 1 d | Component_Diagram.png | Done |
| 2.4 | Write one-page architecture justification | 2.3 | 0.5 d | Justification PDF | Done |
| 3 | Project Setup & Management |  |  |  |  |
| 3.1 | Create GitHub repository MyProject_ShowcaseApp and folder structure | — | 0.25 d | Repository | To do |
| 3.2 | Create Jira project, epics and user stories | 1.4 | 0.5 d | Jira board | To do |
| 3.3 | Capture creation screenshots (GitHub and Jira) | 3.1, 3.2 | 0.25 d | Folder 3 screenshots | To do |
| 4 | Documentation |  |  |  |  |
| 4.1 | Write SRS | 1, 2 | 1 d | SRS document | Done |
| 4.2 | Prepare WBS (this document) | 4.1 | 0.5 d | WBS document | Done |
| 4.3 | Write README and upload all folders | 4.2, 3.1 | 0.25 d | README.md | To do |
| 5 | Later Phases (not part of this submission) |  |  |  |  |
| 5.1 | Copilot-generated code evidence (folder 5) | 2 | TBD | Screenshots / repo link | Later |
| 5.2 | Software testing practice and bug fix (folder 6) | — | TBD | Fixed repo link | Later |